## Slide 1: Bel Air Dam Removal Community Meeting
December 5, 2023

## Slide 2: Agenda
Project Background
Alternatives Analysis
Working Drafts of Current Stream Layout/Profile
Existing Conditions
Dam Ongoing Inspection and Maintenance
Emergency Action Plan
Proposed Conditions
Anticipated Impacts
Environmental Justice
Mitigation
Restoration of Downstream Parcel
Permitting
Schedule

## Slide 3: Project Background

## Slide 4: DCR Abandoned Dams Program
Lowes Pond Dam, Oxford
Monument Pond Dam, Freetown
Factory Village Pond Dam, Ashburnham
Bird Pond Dam, Walpole
Bel Air Dam, Pittsfield
Barre Reservoir Dam, Barre
These 6 are some of the many abandoned dams with no active ownership in the state. These were prioritized because they are the highest risk to the public as all are Significant or High Hazard dams in Unsafe to Poor condition. Currently Dam Safety inspects each dam regularly and hires contractors to perform maintenance as needed at Commonwealth’s cost. Currently none comply with Dam Safety Regulations.

## Slide 6: Bel Air Dam Pittsfield

## Slide 7: Phase II Investigation and Alternatives Analysis Components – 2019 -2020
Condition Assessment
Topographic / Bathymetric Surveys
Subsurface Investigation
Spillway Adequacy Evaluation
Seepage and Stability Evaluation
Sediment Sampling and Management Plan
Develop Alternative Concepts / Costs (Repair, Partial Removal, Full Removal)

## Slide 8: Alternatives Analysis
No Action
Repair
  Restoration of dam to meet Massachusetts Dam Safety Regulations
  Sediment removal
  Ongoing operation and maintenance of a High Hazard Dam
  Requires Municipal or other Owner Commitment to Achieve Property Ownership
Partial Removal
  Reducing height of dam and storage capacity of spillway
  Result in reclassification as non-jurisdictional
  Full Dam Removal
  Generally Preferred Given No Municipal Interest in Dam Repair

## Slide 9: Bel Air Dam, Pittsfield, MA
Built in 1832
Used for power generation for a woolen mill until 1920s
Owner is deceased
Combined earthen embankment, stone masonry, and concrete structure
Height of 26.5’, 200’ long with a capacity of 56 acre-feet
Upstream of several businesses, residences and roads
Failure may cause loss of life and substantial damages
High hazard dam classification
Unsafe condition and Structurally Deficient
City in support of dam removal – preferred alternative
Current dam removal cost estimate: Approximately $19MM
View of auxiliary spillway from
downstream side of dam.
View of sluiceway from
downstream side of dam.

## Slide 10: Existing Conditions

## Slide 11: Ongoing Inspection and Maintenance
DCR Office of Dam Safety (ODS) periodically inspects dam and includes Bel Air Dam in their patrols
Inspected in May 2023 and again following storm event on July 19, 2023
Next inspection scheduled for December 2023
DCR ODS has conducted minor repairs and maintenance as needed
  Added riprap slope protection to a section of the center embankment’s downstream slope to stabilize sluiceway discharge
  Debris is removed as needed from sluice gate openings to maintain minimum water level

## Slide 12: Emergency Action Plan
2017 Emergency Action Plan (EAP)
Emergency Preparedness Document serves as a guide to local and state emergency responders in event of a possible failure
EAP on file with the City Emergency Management Agency, Massachusetts Emergency Management Agency, and DCR Office of Dam Safety
EAP identifies notifications to inform first responders and other applicable agencies
EAP includes description of potential inundation area that may be impacted in the event of failure, which can be used for evacuation planning purposes

## Slide 13: Existing Conditions

## Slide 16: Existing Sediment
Sediment currently below water, but will be above water after dam removal and subject to MCP reporting requirements after dam removal
Exceedances
  Chromium
  Arsenic
  Lead
  PAHs
  EPHs
Disposal required out of state

## Slide 17: Proposed Conditions
Removal of dam spillway and appurtenant structures
Restoration of approximately 1200 feet of the existing streambed of the West Branch of the Housatonic River
  Bank grading, stabilization, and reconstruction of a low-flow channel
Ecological restoration of wetland/floodplain habitat adjacent to the channel
Dredging of 35,500 CY of contaminated sediment

## Slide 18: Current Working Draft of Restored Stream Layout

## Slide 19: Current Working Draft of Restored Stream Profile

## Slide 20: Current Working Draft of Restored Stream Profile

## Slide 21: Current Working Draft of Typical Section

## Slide 22: Proposed Impacts
Temporary and permanent impacts to wetland resource areas
Currently no known impact to Historic and Archaeological Assets of the Commonwealth – consultation with MHC and THPOs pending
Impoundment adjacent to the dam removed to create new stream channel
Temporary sediment stockpiling
Construction period traffic, sidewalk, noise, and air quality impacts

## Slide 23: Wetland Resource Area Impacts
Bank
All existing Bank impacted due to creation of new streambed
Bordering Land Subject to Flooding (BLSF)
Net increase in BLSF due to change in stream alignment/loss of LUW
Bordering Vegetated Wetland (BVW)
BVW loss due to stream reconstruction
BVW habitat restored along new Bank
Land Under Water (LUW)
Permanent LUW loss due dam removal, reducing impoundment
200-foot Riverfront Area
- Increase due to impoundment removal and restoration of natural stream alignment

## Slide 24: Environmental Justice Communities

## Slide 25: Limited English Proficiency Populations

## Slide 26: EJ Impacts
Currently, dam failure would cause significant property damage and potential loss of life
Project will benefit EJ populations due to the removal of an unsafe dam
Project will also remove contaminated sediment, restore natural hydrology, and contribute to restoration of West Branch of the Housatonic River
No expected long-term negative environmental or public health impacts
Short-term construction impacts
  Noise
  Air quality – emissions and dust
  Traffic

## Slide 27: Mitigation
Traffic/Pedestrian Management Plan
Daytime/Work week construction hours
Dust mitigation
Air quality monitoring
Silt fences, straw bales, and turbidity controls
  Around sediment stockpiles
  Around phased in-water work
Habitat restoration/Sediment stabilization
  Tree and shrub planting
  Seeding
  Restoration of wetland habitat

## Slide 28: Downstream Parcel – 370 Waconah Street
Currently not owned by City of Pittsfield
Previous owner, Barry Hollister, is deceased
Vacant since 1986
Concrete slabs of former mill buildings remain; buildings removed in 2009
Phase I and II Site Assessments identified arsenic and cadmium above MCP Reporting Levels
Method 1 Risk Assessment determined No Significant Risk to human health, public safety, public welfare and the environment
Anticipated to be used for staging during dam removal
City plans to redevelop for light industrial use

## Slide 29: Permitting Requirements
Massachusetts Environmental Policy Act
Pittsfield Conservation Commission/Mass DEP WPA NOI
MassDEP 401 Water Quality Certification
US Army Corps of Engineers Section Clean Water Act Section 404 Pre-Construction Notification (PCN)
MassDEP Chapter 91 License
FEMA Conditional Letter of Map Revision
Massachusetts Historical Commission Project Notification Filing
USFWS Endangered Species Consultation

## Slide 30: Tentative Schedule*
MEPA Submittal: January 2024 (initiates official public comment period)
Additional Geotechnical Analysis: January 2024
USACE PCN Submittal: March 2024
FEMA CLOMR Submittal: Spring 2024
Final EIR and State/Local Permit Application Submittals: Spring 2024
Final Design: Spring - Fall 2024
Bidding: Winter/Spring 2025
Construction: Summer 2025
*Schedule dependent on weather and regulatory agency review timeframes and may be extended such that construction would begin in spring 2026

## Slide 31: Bel Air Dam Removal
September 5, 2023